## Phase 2 Task Status
Task | Detailed Activities | Deliverable | Status | Details
Prepare Phase 2 sample data and rules | Prepare CUSTOMER, SUPPLIER, PRODUCT sample staging records; | Phase 2 seed data pack | Implemented | db_phase2_seed.sql and db_phase2_seed_rules.sql seed sample staging entities, canonical fields, transformation rules, and standardization rules for CUSTOMER, SUPPLIER, and PRODUCT.
Create canonical model tables | Create canonical_fields/canonical_models tables with tenant_id, | Canonical data model migration | Implemented | Database migration db_phase2_migration.sql establishes the canonical_fields table with multi-tenancy constraints.
Build canonical model APIs | Implement CRUD APIs for canonical models with validation for | Canonical model APIs | Implemented | CRUD routers inside canonical_models.py, Pydantic schemas, and CanonicalService logic.
Create mapping and rule tables | Create field_mappings, transformation_rules, | Mapping and rules schema | Implemented | Tables field_mappings, transformation_rules, and standardization_rules are created in db_phase2_migration.sql.
Implement field mapping service and APIs | Implement source-to-canonical mapping APIs, duplicate mapping | Field Mapping backend APIs | Implemented | Built in field_mappings.py router, mapping_service.py, and integrated with the frontend in mappingService.ts.
Implement transformation and standardization rules | Build reusable functions: trim_spaces, uppercase, lowercase, | Transformation & standardization service | Implemented | Reusable functions are built inside MDM_Backend/utils/mdm_phase2/ in transformers.py (trim, upper, lower, regex search/replace, and date conversions) and standardizers.py (value translation mappings).
Build normalization execution engine | Read READY_FOR_MAPPING staging records, apply field | Normalization engine | Implemented | Normalization workflow is defined in normalization_service.py and run asynchronously as a background task under the Celery task runner in normalization_worker.py.
Create DQ tables and reference data | Create data_quality_rules, data_quality_runs, | DQ schema migration | Not Started | No database tables or migration scripts exist for data_quality_rules or data_quality_runs.
Load DQ seed rules and reference data | Load initial CUSTOMER rules for not-null, email format, phone | DQ seed rule pack | Not Started | No seed rules exist for data quality.
Build DQ rule management APIs | Implement CRUD APIs for DQ rules, validation by rule_type, | DQ Rule APIs | Not Started | No API endpoints or routes exist for DQ rules.
Build DQ execution and scoring engine | Implement NOT_NULL, FORMAT_CHECK, REFERENCE_CHECK, | DQ execution engine | Not Started | No execution engine code currently checks NOT_NULL, FORMAT_CHECK, or REFERENCE_CHECK.
Implement steward review routing for DQ | Route WARNING/FAILED records to NEEDS_STEWARD_REVIEW, | DQ stewardship backend | Not Started | No routing filters or state machines exist to route records to a stewardship dashboard based on DQ flags.
Create enrichment data model | Create enrichment_sources, enrichment_rules, enrichment_runs, | Enrichment schema migration | Not Started | No enrichment tables or models exist in the database.
Load enrichment source and rules seed | Seed DnB source record, CUSTOMER enrichment rule, provider | Enrichment seed data pack | Not Started | No enrichment rule seeds exist.
Build enrichment provider adapter | Create provider interface, DnB adapter placeholder/mock | Provider adapter framework | Not Started | No provider adapters or mock frameworks exist.
Build enrichment execution engine | Select DQ-passed or approved records, call provider adapter, | External enrichment engine | Not Started | No enrichment runner exists.
Create matching and entity group tables | Create match_rules, match_runs, match_candidates, | Matching schema migration | Not Started | No match rules, runs, or candidates tables exist.
Load match rules and thresholds | Seed CUSTOMER rules: exact email, exact tax/GST, DUNS exact, | Matching seed rule pack | Not Started | No match rule seeds exist.
Implement exact and deterministic matching | Implement exact match logic for source_record_id, email, phone, | Exact matching engine | Not Started | No deterministic exact match algorithms are implemented (only simulated scores are used in the Phase 1 placeholder ingestion pipelines).
Implement fuzzy matching and scoring | Implement fuzzy name/address matching, token normalization, | Fuzzy matching engine | Not Started | No fuzzy matching engine exists.
Create entity groups and resolution | Generate entity_groups and entity_group_members for | Entity group and resolution backend | Not Started | No entity group resolution models/services exist yet.
Maintain dev/staging environment | Ensure backend, frontend, database, queue/worker, object | Stable development/staging environment | Active | Active environment supporting live API servers, Vite development, Redis task workers, and build compilations.